## Risk Register
PINNACLE LENDING SOLUTIONS
Information Security Risk Register ¦ Framework: NIST Cybersecurity Framework (CSF) 2.0 & ISO/IEC 27001:2022
Prepared by: Marcus Albright, GRC Analyst ¦ Review Date: June 2026 ¦ Classification: Internal
Risk ID | Risk Category | Risk Description | Threat Source | Affected Asset / Process | NIST CSF Function | NIST CSF Category (ID) | ISO 27001 Annex A Control | Likelihood (1–5) | Impact (1–5) | Risk Score (L×I) | Risk Level | Existing Controls | Control Gap / Deficiency | Recommended Remediation | Risk Owner | Target Date | Status
R-001 | Data Protection | Unauthorized access to borrower PII stored in LOS/CRM | Malicious insider / external attacker | Loan Origination System (LOS), CRM | Protect (PR) | PR.AC-1 — Identity Mgmt & Access Control | A.9.2 — User Access Management | 4 | 5 | 20 | Critical | Role-based access control in LOS; basic password policy | No MFA enforced; access reviews not documented quarterly | Implement MFA for all LOS/CRM access; conduct quarterly access reviews; log all PII access events | IT / Compliance Officer | Sep 2026 | Open
R-002 | Regulatory Compliance | GLBA Safeguards Rule — incomplete written information security program | Regulatory audit | Compliance Program | Govern (GV) | GV.PO-1 — Organizational Policy | A.18.1 — Compliance with Legal Requirements | 3 | 5 | 15 | High | Informal data handling procedures; annual compliance training | No documented WISP; no annual risk assessment on file | Draft and ratify a GLBA-compliant Written Information Security Program (WISP); schedule annual risk assessment | Compliance Officer / Legal | Aug 2026 | Open
R-003 | Third-Party / Vendor Risk | Mortgage broker or title company exposes NPI through insecure data transfer | Third-party vendor | Vendor data exchange, email/SFTP | Identify (ID) | ID.SC-2 — Supply Chain Risk Mgmt | A.15.1 — Supplier Relationships | 3 | 4 | 12 | High | Vendor contracts include data-handling clauses | No formal vendor risk assessments; no security questionnaire process | Implement annual vendor risk assessments and security questionnaires for all vendors handling NPI | Operations / Compliance | Oct 2026 | Open
R-004 | Endpoint Security | Loan officer laptop lost or stolen — unencrypted borrower data exposed | Physical theft / loss | Endpoint devices (laptops, mobile) | Protect (PR) | PR.DS-1 — Data-at-Rest Protection | A.8.3 — Media Handling | 3 | 4 | 12 | High | Antivirus on company devices; remote wipe capability | Full-disk encryption not verified on all endpoints; BYOD policy absent | Enforce full-disk encryption (BitLocker/FileVault); establish BYOD policy; enable remote wipe on all devices | IT Manager | Aug 2026 | In Progress
R-005 | Phishing / Social Engineering | Loan officer or processor clicks phishing email — credential compromise | External attacker (email-based) | Email system, employee credentials | Protect (PR) | PR.AT-1 — Awareness & Training | A.7.2 — Information Security Awareness | 4 | 4 | 16 | Critical | Annual security awareness training | No simulated phishing program; training not role-specific | Launch quarterly phishing simulations; implement role-based security awareness training for mortgage staff | HR / IT Security | Sep 2026 | Open
R-006 | Access Control | Terminated employee retains system access after offboarding | Insider threat (involuntary) | LOS, CRM, email accounts | Protect (PR) | PR.AC-4 — Access Permissions Mgmt | A.9.2.6 — Removal of Access Rights | 2 | 5 | 10 | High | HR triggers IT ticket on termination | No SLA for access revocation; no automated deprovisioning; audit trail gaps | Define 24-hour access revocation SLA; automate deprovisioning via HR/IT integration; log all offboarding actions | HR / IT | Jul 2026 | Open
R-007 | Incident Response | Security incident with no documented IR plan — extended exposure window | Any threat actor | All systems and customer data | Respond (RS) | RS.RP-1 — Response Planning | A.16.1 — Mgmt of Info Security Incidents | 3 | 5 | 15 | High | Informal escalation to IT manager | No written Incident Response Plan; no tabletop exercises conducted | Develop and ratify an Incident Response Plan; conduct annual tabletop exercise; define escalation roles | CISO / Compliance Officer | Sep 2026 | Open
R-008 | Network Security | Unsegmented network — compromise of one system enables lateral movement | External attacker / malware | Internal network, server infrastructure | Protect (PR) | PR.AC-5 — Network Integrity Protection | A.13.1 — Network Controls | 2 | 4 | 8 | Medium | Firewall at perimeter; basic network monitoring | No network segmentation; no VLAN separation between LOS servers and general staff | Implement network segmentation; deploy IDS/IPS; restrict LOS server access to authorized VLANs only | IT Manager | Nov 2026 | Open
R-009 | Cloud & SaaS Security | Misconfigured cloud storage exposes borrower documents | Misconfiguration / external attacker | Cloud storage (AWS S3 / SharePoint) | Protect (PR) | PR.DS-5 — Protections Against Data Leaks | A.13.2 — Information Transfer | 2 | 5 | 10 | High | Cloud storage in use; basic access controls | No cloud security posture review; bucket/container permissions not audited | Conduct cloud configuration review; enable S3 bucket policies blocking public access; schedule quarterly posture audits | IT / Compliance | Oct 2026 | Open
R-010 | Business Continuity | Ransomware encrypts LOS — pipeline halted, closings delayed | Ransomware group | LOS, file servers, email | Recover (RC) | RC.RP-1 — Recovery Planning | A.17.1 — IT Continuity | 2 | 5 | 10 | High | Daily backups to local NAS | Backups not tested; no offsite/cloud backup; no BCP documented | Implement 3-2-1 backup strategy; test restoration quarterly; document Business Continuity Plan | IT Manager / COO | Oct 2026 | Open
R-011 | Data Retention & Disposal | Improper disposal of physical loan files exposes borrower NPI | Physical security failure | Physical loan files, printed documents | Protect (PR) | PR.DS-3 — Asset Management During Disposal | A.8.3.2 — Disposal of Media | 2 | 3 | 6 | Medium | Shredding bin in office | No documented retention schedule; no certificate of destruction for sensitive files | Implement documented data retention policy; require certificates of destruction; cross-cut shredder mandate | Compliance Officer / Office Manager | Aug 2026 | In Progress
R-012 | Authentication | Weak or reused passwords enable brute-force account takeover | External attacker | All authenticated systems | Protect (PR) | PR.AC-7 — User Authentication Strength | A.9.4 — System & Application Access Control | 3 | 4 | 12 | High | Password policy exists; minimum length enforced | No password manager mandated; complexity rules inconsistent across systems; no MFA on email | Enforce MFA on email and core systems; mandate password manager; standardize complexity policy | IT Manager | Aug 2026 | Open
R-013 | Audit Logging & Monitoring | No centralized log monitoring — security events go undetected | Any threat actor | LOS, CRM, network devices | Detect (DE) | DE.CM-1 — Network Monitoring | A.12.4 — Logging & Monitoring | 3 | 4 | 12 | High | Individual system logs exist; ad hoc review | No SIEM or centralized log aggregation; no alerting on anomalous events | Deploy SIEM (Wazuh or Splunk); aggregate LOS, CRM, and network logs; configure alerting for critical events | IT Security / Compliance | Dec 2026 | Open
R-014 | CFPB Regulatory Exposure | CFPB data-handling violation due to inadequate controls on consumer data | Regulatory enforcement | Consumer financial data, loan files | Govern (GV) | GV.PO-2 — Risk Strategy | A.18.1.4 — Privacy of Personal Information | 2 | 5 | 10 | High | CFPB training in onboarding; compliance officer oversight | No formal data mapping of consumer data flows; no periodic CFPB controls review | Map all consumer data flows; document CFPB control obligations; schedule annual compliance review | Compliance Officer / Legal | Sep 2026 | Open
R-015 | Privileged Access Management | IT admin credentials compromised — full environment access granted to attacker | External attacker / malicious insider | Server infrastructure, all systems | Protect (PR) | PR.AC-6 — Identities Proofed & Bound | A.9.2.3 — Mgmt of Privileged Access | 2 | 5 | 10 | High | Admin accounts exist; passwords changed periodically | No PAM solution; shared admin credentials in use; privileged activity not logged | Eliminate shared admin credentials; implement PAM solution; log all privileged access and review monthly | IT Manager / CISO | Nov 2026 | Open
RISK SCORING LEGEND
Critical |  | ≥ 16 | Risk Score = Likelihood × Impact
High |  | 10 – 15 | Risk Score = Likelihood × Impact
Medium |  | 5 – 9 | Risk Score = Likelihood × Impact
Low |  | 1 – 4 | Risk Score = Likelihood × Impact

## Risk Summary
PINNACLE LENDING SOLUTIONS — Risk Register Summary
Risk Level | Count | % of Total | Highest Risk ID(s) | Priority Action
Critical | 1 | 7% | R-001 | Enforce MFA + quarterly PII access reviews
High | 6 | 40% | R-002, R-006, R-007, R-009, R-010, R-014 | Document WISP; build IR Plan; enforce offboarding SLA
Medium | 8 | 53% | Multiple — see register | Phishing simulation; SIEM deployment; vendor risk program
Low | 0 | 0% | N/A | N/A
TOTAL | 15 | 100%